## List
KERALA PUBLIC WORKS DEPARTMENT
PWD ROADS DIVISION, KOLLAM
PROGRESS REPORT OF BUDGET WORKS FOR THE MONTH OF OCTOBER 2019
Sl.No | LA Constituency | Name of Project | Estimate Amount | A.S No. Date & Amount
CHADAYAMANGALAM CONSTITUENCY
Budget 16-17
1 | Chadayamangalam | Budget work 2016-17.Providing improvements to Chengamanad Kadakkal Road (Anchal Kurisinmoodu to Kadakkal .Ch.16/690 to 29/410 by Providing BM & BC . | 660 | G.O.(Ms) No. 18/2017/PWD dt 16.03.17 for Rs. 660 Lakhs
2 | Chadayamangalam | Budget work 2016-17. Improvements to Chithara Pangodu road by providing BM & BC Km.0/000 to 5/500 . | 265 | G.O.(Ms) No. 18/2017/PWD dt 16.03.17 for Rs. 265 Lakhs
|  | Total | 925
Budget 17-18
1 | Chadayamangalam | Budget works 2017-18. Improvements to Mullikkadu - Kollayil road. BM & BC | 150 | G.O.(Rt) No.1386/ 2017/PWD dt 15.09.17 for Rs.150.00 Lakhs.
2 | Chadayamangalam | Budget works 2017-18. Improvements by providing DGBM & BC to Velinalloor Temple Road. | 135 | G.O.(Ms) No.9/2018/PWD dt 28.03.18 for Rs. 135.00 Lakhs.
3 | Chadayamangalam | Budget works 2017-18.Budget works 2017-18 Improvements by providing DGBM & BC to Karinganoor-Attoorkonam-Pallickapuzhakadavu road from 0/00 to 3/300. | 250 | G.O.(Ms) No.9/2018/PWD dt 28.03.18 for Rs. 250.00 Lakhs.
4 | Chadayamangalam | Budget works 2017-18. Improvements by providing DGBM & BC to Anchal-Kadavaram road 0/00 to3/00 | 295 | G.O.(Ms) No.9/2018/PWD dt 28.03.18 for Rs. 295.00 Lakhs.
5 | Chadayamangalam | Budget works 2017-18. Improvements to Chadayamangalam - Pallikkal road using 30mm BC | 100 | G.O.(Ms) No.9/2018/PWD dt 28.03.18 for Rs. 100.00 Lakhs.
|  | Total | 930
Budget Work 2019-20
1 | Chadayamangalam | Budget Work 2019-20 Improvements to Attupuram Missionkunnu Azhanthakuzhy road. | 300 | AS obtained under Rs.100 Token Provision
|  | Total | 300
Sabarimala 2016-17
1 | Chadayamangalam | S/F 2016-17 Providing 20mm CC to TS Road from Km.43/000 to 44/300 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
2 | Chadayamangalam | S/F 2016-17 Providing 20mm CC to TS Road from Km.44/700 to 45/800 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
3 | Chadayamangalam | S/F 2016-17 Providing 20mm CC to TS Road from Km.46/000 to 47/000 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
4 | Chadayamangalam | S/F 2016-17 Providing 20mm CC to TS Road from Km.47/500 to 49/000 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
5 | Chadayamangalam | S/F 2016-17 Providing 20mm CC to TS Road from Km.49/300 to 50/500 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
6 | Chadayamangalam | S/F 2016-17 Providing 20mm CC to TS Road from Km.50/700 to 52/000 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
7 | Chadayamangalam | S/F 2016-17 Providing 20mm bit CC to - Chengamanadu - Kadakkal Road from Km.27/000 to 29/300 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
8 | Chadayamangalam | S/F 2016-17 Providing 20mm bit CC to ParippallY - Madathara Road from Km.20/000 to 22/000 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
9 | Chadayamangalam | S/F 2016-17 Providing traffic saftey works to Parippally - mMadathar Road from Ch 16/200 to 33/097 and TS Road 43/000 to 52/000 | 20 | Order No. CE/R&B/GL/AEE-II/SF/2016 dated 29.07.16. (Kollam-for 21 Roads for Rs. 430 Lakhs) A.S No.-G.O. (Rt) No. 56/2016/PWD dt 28.07.16
|  | Total | 180
Sabarimala 2017-18
1 | Chadayamangalam | Sabarimala 2017-18 :Providing 20mm chipping carpet to Mullikkadu Kollayil Road 0/000 to 4/200. | 20 | A.S. No.Order No. CE/R&B/GL/AEE-II/SF/2017 DATED 25.08.17…. G.O.(M.S).No. 47/2017/PWD dt 25.08.17 TOTAL 41 WORKS FOR RS. 1864 LAKHS.
2 | Chadayamangalam | Sabarimala 2017-18 : Providing 20mm chipping carpet to Ayirakkuzhy Anchal Road Road 0/000 to 2/500. | 21 | A.S. No.Order No. CE/R&B/GL/AEE-II/SF/2017 DATED 25.08.17…. G.O.(M.S).No. 47/2017/PWD dt 25.08.17 TOTAL 41 WORKS FOR RS. 1864 LAKHS.
3 | Chadayamangalam | Sabarimala 2017-18 : Providing 20mm chipping carpet to Parippally - Madathara Road from Nilamel to Kadakkal. | 25 | A.S. No.Order No. CE/R&B/GL/AEE-II/SF/2017 DATED 25.08.17…. G.O.(M.S).No. 47/2017/PWD dt 25.08.17 TOTAL 41 WORKS FOR RS. 1864 LAKHS.
4 | Chadayamangalam | Sabarimala 2017-18 : Providing 20mm chipping carpet to Parippally - Madathara Road from Kadakkal to Madathara . | 24 | A.S. No.Order No. CE/R&B/GL/AEE-II/SF/2017 DATED 25.08.17…. G.O.(M.S).No. 47/2017/PWD dt 25.08.17 TOTAL 41 WORKS FOR RS. 1864 LAKHS.
|  | Total | 90
Sabarimala 2018-19
1 | Chadayamangalam | Sabarimala Festival - 2018-19. Providing Maintenance by BC overlay and other allied works to Parippally - Madathara Road from Nilamel to Madathara Km. 16/100 to 33/100. | 450
2 | Chadayamangalam | Sabarimala Festival 2018-19. Providing 20mm bit Chipping carpet to Mullikkadu - Kollayil Ch.0/000 to 2/000. | 15
3 | Chadayamangalam | Sabarimala Festival 2018-19. Providing 20mm bit Chipping carpet to Mullikkadu - Kollayil Km.2/400 to 4/200 except the portion covered in the culvert construction. | 15
4 | Chadayamangalam | Sabarimala 2018-19 : Providing 20mm bit Chipping carpet to Alenchery- Onthupatcha Road ch 12/500 to 18/600km . | 22
5 | Chadayamangalam | Sabarimala 2018-19 : Providing 20mm bit Chipping carpet to Alenchery- Onthupatcha Road ch 0/000 to 4/000. | 10
|  | Total | 512
Nabard 2018-19
1 | Chadayamangalam | NABARD RIDF XXIV-2018-19-Improvements to Veikkal – Marankuzhi – Vattappara road Ch. 0/000 to 2/500, Alumkunnil – Perumiliyil road Ch. 0/000 to 1/950 from Nilamel Panchayat of Kollam Dist. Chadayamangalam LAC+Attingal LAC. 4.450 km | 514 | GO(Rt)No.1777/2018/PWD dated 15.11.2018
|  | Total | 514
Flood Damages 2018-19
1 | Chadayamangalam | Improvements and Providing DGBM&BC and allied works to Adayamon-Tholikkuzhy Road 4/440 to 6/640(Mukkunnam to Moonnu kallin mood) | 160 | GO(Rt)No.1978/2018/PWD dated 22.12.2018
2 | Chadayamangalam | FDR 2018-19Construction of Retaining walla at damaged portion of Chengamanad kadakkal road ch 22/440 and providing 20mm CC to vayala Manappara road ch 0/000 to 1/000 | 140 | GO(Rt)No.1978/2018/PWD dated 22.12.2018
|  | Total | 300