## 2016-17
CONSTITUENCY WISE LIST OF ROAD WORKS SANCTIONED DURING THIS MINISTRY WITH PRESENT STATUS
Sl. No | Name of work | Amount of work in Lakhs | Present Status of work
Division:Ernakulam(PLAN works)
Constituency: Aluva
1 | Budget Work 2016-17 Improvements to Aluva Town limit Road | 77 | Work completed
2 | Budget Work 2016-17 Resurfacing with close grade premix carpet of 20mm thickness to Carmal Manakkapady Road ch. 1/500 to 3/800 Km | 16.75 | Work completed
3 | Budget Work 2016-17 Resurfacing with close grade premix carpet of 20mm thickness to Chowara Mangalapuzha road ch. 0/00 to 1/800 | 20.5 | Work completed
4 | Providing drainage facilities in Aluva Munnar road ch 6/000 to 8/000 | 23 | work completed
5 | Budget Work 2016-17 Resurfacing with close graded pre mix carpet of 20mm thickness to Chathapuram Idayapuram societypady road ch 1/000 to 2/600 | 21.7 | work completed
6 | Resufacing with BM & BC to Thottumukkam Thadiyittparambu road ch 0/000 to 2/000 | 94 | BM and Bc work from Ch. 1/000 to 2/000 completed and Balance BM and BC work to be arranged after the DLP of restoration work.
7 | Resurfacing with close graded premix carpet to Thottumukham Erumathala road ch 0/900 to 2/900 | 17.95 | work completed
8 | Budget Work 2016-17 Resurfacing with close graded premix carpet of 20mm thickness to Edathala Thayikattukara road km 0/000 to 3/000 | 27.1 | work completed
9 | Budget Work 2016-17 Resurfacing to Ilayaraja Palace road ch 0/000 to 2/500 | 22.05 | work completed
10 | Budget work 2016-17 - Resurfacing and construction of drain to Angamaly - Paravoor road ch 3/500 to 5/400 (1900m) | 43.45 | This work under the control of Angamali section and work not started yet due to the delay in dem,arking of boundary.
11 | Aluva LAC - Budget work 2016-17 - Resurfacing with BM & BC to and construction of box culvert in Kuttamassery Chungamveli road ch 0/000 to 4/000 | 187.5 | Box culvert and BM and BC work from 1/940 to 4/000 completed. Restoration works from 0/000 to 1/940 partially completed. Balance BW to be arranged.
Constituency: Angamaly |  | 551
1 | Improvements to Sreesankara College road ch. 0/000 to 1/500 by Providing CC drain and BM & BC ( Proposed 20mm chippng carpet instead of BM & BC) | 8.65 | Work completed
2 | Improvements to by providing BM & BC to Angamaly Railway station road ch. 0/000 to 0/200 | 27.58 | Work completed.
3 | Improvements to Vengoor Nayathodu road ch. 0/300 to 3/500 | 27.65 | work completed
4 | Improvements to Manjapra _ Malayattoor road and F.I.T Kannimangalam Road ch 0/000 to 2/200 (Chandrapuzha Jn to Naduvattom Jn) by providing CC drain and 20mm chipping carpet | 30.95 | Work completed
5 | Improvemnts to NH link road ch 0/000 to 0/800 and Angamaly Market landing road ch 0/000 to 0/800 providing CC drain and BM & BC | 58.3 | Work completed
6 | Improvements and providing BM & BC to Angamaly Manjaly (Via Madurappuram) at ch 0/000 to 0/600Km | 188.7 | Initial level calculation in progress
7 | Improvements to Karukuty - Azhakam road ch 0/000 to 5/000 | 72.67 | Work completed
8 | Improvements to Manjapra - Chully road ch 0/000 to 6/000 km (providing CC tile and close graded premix) | 38.8 | work completed
9 | BW 2016-17;Improvements to Cheranallore Trace Road ch:0/000 to 2/270km with BM & BC including drainage facilities in Angamaly LA | 94.3 | work completed
10 | BW 2016-17;Improvements to Cheranallore Trace Road ch:0/000 to 2/270km with BM & BC including drainage facilities in Angamaly LA | 290 | tile work completed
Constituency:Kalamassery |  | 837.6
1 | Providing drainage facilities at various chaniages of road around Cochin University | 54 | work completed
2 | Providing drainage facilities at various chainages of North Kalamassery Glass Factory road | 56.46 | work stand still..balance portions work could not be done due to the dispute from the public.Work to be closed
3 | Providing drainage facilities at Muppathadam junction to Panchayath Junction of UC College Edayar road | 54.6 | work completed.
4 | Construction of new drain at ch 0/500 to 1/500 of Manjummel Muttar road | 70.7 | Closure agreement to be executed
Constituency:Ernakulam |  | 235.76
1 | Improvements to Kutty Sahib road ch 0/000 to 2/000 | 187.55 | Work Completed.
2 | Improvemnts to Old NH ch 354/400 to 355/300 | 164.75 | Work Completed.
3 | Budget work 2016-17 - Improvements to Banerji road ch 0/000 to 0/900 | 118.7 | Work Completed.
4 | Budget work 2016-17 - Improvements to MG road ch 9/000 to 11/000 | 221 | Work Completed.
Constituency:Kochi |  | 692
1 | B/w 16-17 Improvements to Kattiparambu Kalathara road Km. 0/000 to 1/500 | 61 | Work completed
2 | Improvements to Town Hall Road providing BM & BC and drainage facilities between ch. 0/000 to 0/650 | 47.5 | Work completed
3 | Providing interlocking tiles at Veli Dronacharya Junction in Jawahar Road at ch. 0/000 | 91.5 | Work completed.
4 | Providing BM & BC to Kumbalanghi Ezhupunna road ch 3/800 to 5/600 | 189.1 | Work completed.
5 | Construction of protection wall and drainage in Pandikudy - Chellanam road ch 8/500 - 8/700 | 44.78 | Work completed.
| Construction of protection wall and drainage in Pandikudy - Chellanam road ch 8/500 - 8/700 | GO No.18/2017/PWD dated16.03.2017for Rs289.9L | Levelling course and tile work in progress. BM and BC after monsoon.
6 | B/W 2016-17 - Improvements to Old NH road from 356/400 to 360/000 | 289.9 | Levelling course and tile work in progress. BM and BC after monsoon.
7 | Budget work 2016-17 - Improvements to PT Jacob road (BM&BC) 0/000 to 1/800 | 66.65 | Completed
8 | Budget work 2016-17 - Improvements to K.J. Harshal road ch 1/500 to 2/900 | 145.72 | Completed
9 | Budget work 2016-17 - Side protection work in Kumbalanghi - Kandankadavu ch 0/000 to 2/500 | 94.55 | Completed
10 | Budget work 2016-17 - Providing 20mm chipping carpet in Chellanam - Ezhupunna road ch 0/000 to 1/100 | 94.35 | Completed
Constituency:THRIKKAKARA |  | 1125.05
1 | Improvements to Vyttila-Palarivattom Road ( Mahakavi Vyloppilly Road) ch. 0/000 to 4/400 | 76.5 | Work completed
2 | Improvements to Palachuvadu - Nilampathinji road km 2/000 to 3/500(Nomenclature changed to 3/400 to 4/600) | 144.8 | work completed
3 | Improvements to Edachira - Vayanasala road ch 0/000 to 2/800 | 224.7 | work completed
4 | Providing BM & BC and drainage facilities to Edappaly Bazar Arakkakadavu road ch 0/000 to 0/900 | 88.7 | work completed
Constituency:TRIPUNITHURA |  | 2350.92
1 | Widening and Improvements to Eroor Kaniyampuzha Road under Roads Section, Thrippunithura ch. 0/800 to 2/280 | 76 | Work completed
2 | B/W 2016-17 Improvements to Udayamperoor Kureekkad road 0/00 to 0/600 | 90.5 | Work completed.Bill submitted
3 | Budget Work 2016-17 Providing drainage facilities and Footpath to Mini byepass road 1/100 to 1/850 | 181 | Work tendered. But kept pending due to CRF work in same reach. Existing TS to be cancelled .For cancellation submitted to CE office.Estimate submitted with new provisions, kept pending for file to return. .
4 | B/W 2016-17 Improvements to Town road and Reconstruction of damaged Drain and footpath (Stable road 0/000 to 0/300, Kanankulangara road 0/000-0/300, Sanskrit road 0/150-0/350, Chakkamkulangara road 0/200 to 0/300, BHS road 0/200 to 0/400 | 271.5 | BM & BC Completed in the Town roads. Drain work in progress.Letter issued to contractor to complete the work by Dec 2019.
5 | Budget work 2016-17 - Improvements to Nadakkavu Mulanthuruthy road ch. 0/000 to 0/800 | 162.9 | Work was delayed due to boundary demarcation. Now as per site visits done revised level submitted and work to start after monsoon .Patch work being attended by the contractor.
6 | Budget work 2016-17 - Widening of Nettoor Panagad Road ch 1/500 to 3/800 | 188.9 | Completed.Bill submitted
7 | Budget work 2016-17 - Widening of Kumbalangahi -Perumpadappu road-Ch.0/000 to 1/800 | 298.2 | LA in progress. Requisition submitted to collectorate on 03.08.2019. MLA has instructed to take up the resurfacing work .Estimate submitted for TS at CE office (price id 4690)
8 | Budget work 2016-17 - Widening of Madavana - Panangad road ch 3/850 to 7/500 | 94.2 | Completed
Constituency:PARAVUR |  | 1363.2
1 | Improvements to NH Byepass at Paravur in Paravur LAC 0/000 to 2/100 | 93 | Work completed
2 | Improvements to Puthenvelikkara - Police Station to Cochin State frontier road Km 0/000 to 2/860 | 142.4 | Work completed
3 | Improvements to Paravur Chathanad road 2nd phase from ch 5/300 to 8/750 | 150.25 | work Completed.
Constituency:VYPIN |  | 385.65
| B/W 201617Improvements to Paravur Cherai Road -Providing BM & BC ( Balance Portion) | 110 | Work completed
| Improvements to Malipuram - Chappa Kadapuram road (Reconstruction of damaged portion from University junction to AS junction) in Vyppin LA Constituency | 403.3 | Work completed
| Widening and Improvements (BM & BC work) to Aniyil Nedungad road Km 0/000 to 5/000 in Vypin LA Constituency | 273 | Work completed
| Budget work 2016-17 - Improvements to Elamkunnapuzha beach road balance portion in Vypin LAC ch 0/750 to 1/500 | 121.35 | Culvert work & WMM completed
| Budget work 2016-17 - Improvements to Iqbal road (BM&BC balance work) ch 0/000 to 1/600 | 273 | Work completed
| Budget work 2016-17 - Improvements (BM&BC) to A.A said Muhammed road Km 0/000 to 1/815 | 220.45 | Work completed
1401.1

## 2017-18
CONSTITUENCY WISE LIST OF ROAD WORKS SANCTIONED DURING THIS MINISTRY WITH PRESENT STATUS
Sl. No | Name of work | Amount of work in Lakhs | Present Status of work
Division:Ernakulam(PLAN works)
Constituency: Aluva
1 | B/W 2017-18 Improvements to Chathapuram Edayapuram Societypady road Ch. 0/000 to 1/000 and 2/900 to 4/000 | 35 | Work completed.
2 | B/W 2017-18 Providing BM & BC surfacing to Kuttamassery Chalakkal Thadiyittaparambu road ch 0/000 to 0/600 | 65 | Work completed.
3 | B/W 2017-18 Improvements to Angamaly - Paravur Road Ch: 1/800 to 3/500 | 260 | Initial levels taken and drain works 100m completed
4 | B/W 2017-18 Improvements to Pallikavala - Ayurveda Dispensary road. | 75 | Work completed.
5 | B/W 2017-18 Improvements to Parambayam - Avanamcode Road Ch: 3/500 to 6/500. | 265 | Widening,drain work and tile work completed. BM and BC work is proposed after monsoon.
6 | Additional Budget works 2016-17 Improvements to Nazareth Carmal Road ch.0/000 to 3/000 | 50 | Work completed.
Constituency: Angamaly |  | 750
1 | B/W 2017-18 improvements to kalady - anappara - Poothamkutty Ch 8/000 to 12/000 | 100 | Work Completed
2 | Additional Budget work 2017-18 Improvements to Blachippara Palissery Road Ch. 4/000 to 6/000. | 25 | Work Completed
3 | Additional Budget Work 2017-2018 Improvements to Mookkannor Ezhattumugham Road Ch.12/000 - 13/000 | 25 | Work Completed
4 | B/W 2017-18 - Improvements to 4th Mile A.A. road Ch: 0/450 to 1/330(Balance portion) | 350 | Drain work in progress
5 | B/W 2017-18 - Providing Interlocking tile in water logging areas in Kariyad - Mattoor road, Airport Junction, Nayathodu Junction, Piraroor Junction, Mattoor Junction. | 90 | Work Completed
6 | B/W 2017-18 Improvements to Vengoor-Nayathodu Road ch.0/300 to 0/900 (improvements in newly acquired land) | 160 | Initial Level taken
7 | B/W 2017-18 Improvements to Vengoor-Kidangoor Road ch.0/000 to 2/800. | 30 | Work Completed
Constituency:Kalamassery |  | 780
1 | B/W 2017-18Improvements to Neerikode Thattampady Road Ch 0/000 to 2/000 | 150
2 | B/W 2017-18 Reconstruction of Akkama Culvert-RCC Box Culvert at Kongorppilly -Olanadu Road | 50
3 | B/W 2017-18 Construction of drain and strengthening of road shouldersof Aluva - Paravaur Road Ch: 3/150 to 11/650. | 89
4 | B/W 2017-18 Improvements and BM & BC surfacing to Kottappuram -Mambra Road ch.0/000 to 1/600 | 114
5 | B/W 2017-18 Improvements and BM & BC surfacing to Thadekkadavu -Aduvassery Road from Thadikkakadavu Jn to Thadikkakadavu Bridge | 221 | clarification to be obtained
6 | B/W 2017-18 Improvements and BM & BC surfacing to Aikya Kerala Mattupuram Road ch.0/000 to 2/000 | 126 | Initial Level taken, drainage work completed
7 | B/W 2017-18 Improvements and BM & BC surfacing to Edayar junction IRE-Ferry Road ch.0/000 to 0/460,Approach road to IRE ch.0/000 to 0/400 and Approach road to Mosque at Edayar ch.0/000 to 0/480. | 100 | Nomencleature of the work to be changed
Constituency:Ernakulam |  | 850
1 | B/W 2017-18 Improvements to Gosree road ch 0/000 to 0/900 | 100 | Work completed
2 | B/W 2017-18 Improvements to Broadway road from ch.0/000 to 1/020 | 292 | SN issued
3 | B/W 2017-18 Improvements to drainage facilities in Chittoor - Moolampilly road ch.0/000 to 1/000 | 42 | Completed
4 | B/W 2017-18 Improvements to drainage facilities in Perandoor-Landing road from ch.1/400 to 2/400 | 220 | Work in progress
5 | B/W 2017-18 Improvements to H.M.C.A-Chitoor Road including drainge rectification works ch.0/000 to 1/000 | 70 | Work completed
6 | B/W 2017-18 Improvements to drainge facilities in vaduthala - Chittoor Road Ch: 0/000 to 1/400. | 50 | Work completed
7 | Additional B/W 2017-18- Improvements to Broadway road by providing interlocking paving tiles from Ch-0/300 to 0/500 | 50 | Work completed
Constituency:Kochi |  | 824
1 | B/W 2017-18 -Improvement of Kumbalangi Ezhupunna Road by BM & BC between ch.0/000 to 3/800 including road towards old Perumpadappu Jetty. | 190 | Retendered . No bidders . Work to be carried by Quotation. (TS cancelled to include GST and estimate resubmitted on July 2019 with Permpaduppu Jetty avoided due to lack of fund. So now AS approval required for change in name. Letter submitted to CE office on 28.08.2019
2 | B/W 2017-18 -Construction of drain in Fr. Mathew Kothakath Road between Ch: 1/360 to 1/800. | 25 | Work completed
3 | B/W 2017-18 -Construction of drain at Right side of Pandikudy - Chellanam road between Ch: 4/950 to 5/100. | 15 | Work completed
4 | B/W 2017-18 Re construction of Damaged culvert in P.T Jacob Road | 75 | Work started .Utility shifting identified . Estimate from KSEB and KWA awaited . Work to re- start after monsoon.
5 | B/W 2017-18 construction of Drain in Pandikudi Chellanam Road Ch.6/250 to 7/000 | 90 | Chequerred Tile laying work in progress
6 | B/W 2017-18 Improvements to Fr.Mathew Kothakath Road by providing BM & BC Ch.0/000 to 1/800 | 100 | Work completed
7 | B/W 2017-18 Improvements to Santo Gopalan Road by providing BM & BC Ch.0/000 to 1/800 | 100 | Levels taken. Work kept pending due to KWA pipe line work.
8 | B/W 2017-18 providing BC in K B Jacob Road Ch.0/000 to 1/900 | 100 | Work completed
Constituency:THRIKKAKARA |  | 695
1 | B/W 2017-18 Improvements to old NH17 Edappally-cheranelloor ch.0/000 to 1/000 | 150 | Nearing completion
2 | Construction of retaining wall in thuthiyoor Seaport -Airport Road at Ch 1/600 | 58.1 | work completed
3 | B/W 2017-18 Improvements to Vennala Palachuvadu Road( ch.0/000 to 1/000), Vennala janatha road (ch.0/000 to 0/600) , Edappally bazar - Arakkakadavu road (ch.0/900 to 4/800 ) and Vytila - Palarivattom road (ch.0/000 to 4/100) | 300 | Retaining wall completed 35% work completed
4 | B/W 2017-18 Improvements to Manimala road ch.0/000 to 1/560 | 110 | Drain work completed
5 | B/W 2017-18 Improvements to Athani- Mundanpalam road ch.0/000 to 2/500 | 196 | Drain work in progress
Constituency:TRIPUNITHURA |  | 814.1
1 | B/W 2017-18 Improvements to Kumbalam Road Ch.0/000 to 3/300 | 200 | Completed bill submitted
2 | B/W 2017-18 Providing BM & BC to Ettumanoor- Ernakulam Road Ch.49/000 to 51/700,46/900 to 48/000,38/500 to 40/000,Elamana Road Ch.0/000 to 0/300,Thamaramkulangara Road 0/000 to 0/550 Anchal office road 0/000 to 0/640, Panamkutty Landing Road 0/000 to 0/350, Kandanad Branch Road 0/000 to 1/600, Kettezhuthu Kadavu road ch.0/650 to 1/100, Eroor Manakapadi Road ch.0/000 to 1/939, BHS Road 0/000 to 0/380 , Chakkam Kukangara road 0/000 to 0/580 ,Sanskrit college road 0/000 to 0/580. | 500 | Revised TS obtained from CE.Tender finalisation under scruitny.Single bidder not agreeing to reduce to to LMR rate. Tender to be cancelled and retendered with new site conditions.
3 | B/W 2017-18 Providing BM&BC and drainage facilities in Kidangu road ch.0/000 to 0/150, Kalikotta road ch.0/000 to 0/805,K T road ch.48/600 to 49/220 and Kodankulangara road ch.0/000 to 0/450 | 100 | Initial levels reported.Slab casting works completed.Drain work in Kodakulnagara Road .Work rescheduled due to monsoon and to be completed by Dec 2019.
4 | B/W 2017-18 Providing CC interlocking tiles between 3/070 to 3/640 (balance portion) in Netoor Panagad road | 40 | Work completed
Constituency:Piravam |  | 840
1 | B/W 2017-18Providing 20mm Chipping carpet to Erathadam-cherukara road from km 0/000 to 6/070 | 42 | Work completed.
2 | B/W 2017-18 Providing 20mm Chipping carpet to Nadakkavu road from km 0/600 to 1/850 | 15 | Work completed.
3 | B/W 2017-18 Improvements to Kottayathupara-Kureekad-Thupampady road ch 2/980 to 6/400 | 15 | Work completed.
Constituency:PARAVUR |  | 72
1 | B/W 2017-18 Improvements to Chendamangalam - Karipayikadavu Road, H.S Chendamangalam to Western Part of Chendamangalam Road and Pazhambillythuruth Road | 150 | Completed
2 | B/W 2017-18 Improvements to Mala-Elanthikara road from ch.0/000 to 2/990 in Paravur LAC | 196 | Work completed
3 | B/W 2017-18 Reconstruction of Kundekadavu Bridge in Paravur- Chathanad Road | 400 | Work comes under Bridges Division
Constituency:VYPIN |  | 746
1 | B/W 2018-19 Improvements (BM&BC)Jaihind Poduval & Church road ch.0/000 to 2/250 | 150 | BM completed
2 | B/W 2018-19 Improvements ( BM&BC) to Elamkunnapuzha-Kizhakke Arattuvazhi Karuthedam road | 120 | Work in progress
3 | B/W 2018-19 Improvements ( BM&BC) to Belbow Junction Valappu Junction road portion from AS Jn to Valappu Jn ch.6/600 to 8/000 | 120 | Completed
4 | B/W 2017-18 Improvements ( BM&BC) to Belbow Junction Valappu Junction road from Belbow Jn to LNG road ch.0/000 to 1/550 | 99 | completed
5 | B/W 2017-18Improvements ( BM&BC) to Light house beach road ch.0/000 to 1/050 | 97 | completed
6 | B/W 2017-18 Improvements ( BM&BC) to Cherai beach road ch.0/000 to 1/550 | 99 | Road furniture works to be completed
7 | B/W 2017-18Improvements ( BM&BC) to Cheruvype road ch.0/000 to 2/100 | 99 | BM & BC Completd
784

## 2018-19
CONSTITUENCY WISE LIST OF ROAD WORKS SANCTIONED DURING THIS MINISTRY WITH PRESENT STATUS
Sl. No | Name of work | Amount of work in Lakhs | Present Status of work
Division:Ernakulam(PLAN WORKS)
Constituency: Aluva
1 | Budget Works 2018-19- Improvements to Old NH Byepass road ch 0/400 to 1/980 | 200 | Retendered with opening as on 20.09.2019
2 | Budget Works 2018-19- Improvements to Herbert Road Ist reach ch 1/000 to 3/700 | 50 | work completed
Constituency: Angamaly |  | 250
1 | Budget Works 2018-19- Improvements to Kalady Anappara Poothamkutty road ch 1/200 to 5/000 ( Balance portion) | 150 | work completed
2 | Budget Works 2018-19- Improvements to Karukutty Ezhattumugham Road ch 5/000 to 7/000 ( Balance portion) | 100 | work completed
Constituency:Kalamassery |  | 250
1 | Budget Works 2018-19- Improvements and BM & BC surfacing to Thattampady Purapallikavu Karumaloor Govt Hospital Road ch 0/000 to 1/800 | 150 | TS to be cancelled and retendered
Constituency:Ernakulam-Nil |  | 150
Constituency:Kochi
1 | Budget Works 2018-19- Providing drainage facilities to Pandikudy Chellanam Road ch 10/500 to 14/000 | 50 | Completed.
2 | Budget Works 2018-19- Providing drainage facilities to Pandikudy Chellanam Road ch 14/500 to 16/700 | 50 | Completed
Constituency:THRIKKAKARA |  | 100
1 | Budget Works 2018-19- Improvements to CEPZ Deviation road ch 0/000 to 0/660 | 100 | Levels taken .Work to be done after monsoon.
Constituency:TRIPUNITHURA
1 | Budget Works 2018-19- Improvements to Cheppanam Chathamma Road 0/000 to 2/300 | 200 | Work had been kept pending due to technical reasons.Now .Estimate submitted for T.S with Price Id 4803 . Now at SE office for TS approval.
Constituency:PARAVUR |  | 200
1 | Budget Works 2018-19- Improvements to Athani Kavilnada Chemmayam Road ch 0/000 to 2/600 in N Paravoor Constituency | 200 | S.N issued to Sri.Benny Thomas.Lowest Contractor @ approved rate from CE-170.32L.The contractor not willing to execute the work at this rate.Quoted rate 194.53L
Constituency:VYPIN |  | 200
1 | Budget Works 2018-19- Improvements and Beautification works to Varapuzha Kadamakudy road ch 3/000 to 5/000 | 300 | Initial levels taken
2 | Budget Works 2018-19- Improvements to Ayyampilly Manapilly road ch 0/000 to 1/000 | 99 | Levels taken
399

## 2019-20
CONSTITUENCY WISE LIST OF ROAD WORKS SANCTIONED DURING THIS MINISTRY WITH PRESENT STATUS
Sl. No | Name of work | Amount of work in Lakhs | Present Status of work
Division:Ernakulam(PLAN WORKS)
Constituency: Aluva
1 | BW-2019-20-Construction of drain at various places in Chengal Chowara road ch.0/000 to 6/000 | 100 | Tendered with opening as on 15.11.2019
Constituency: Angamaly-nil |  | 100
Constituency:Kalamassery
1 | B/W 2019- 20 Improvements and BM&BC Surfacing to Chirayam Methanam Panayikulam Road ch 0/500 to 2/000 | 150 | TS estimate under scrutiny
Constituency:Kochi
1 | B/W 2019-20 Improvements to Harbour bridge approach | 100 | Estimate under preparation
Constituency:THRIKKAKARA |  | 100
1 | B/W 2019-20 Construction of new culvert in Edapally Bazar Arkkakaduv Road near YMCA | 50 | TS estimate under scrutiny
Constituency:TRIPUNITHURA
1 | Budget work 2019-20 - Improvements to various roads under Thripunithura Constituency (Improvments to Elammana Road0/000 to 0/300, West BHS road 0/000 to 0/380 and Mamala Branch Road0/000 to 1/600) | 150 | Tendering procedure in progress with Price Id 4211, now at SE office.
2 | Budget work 2019-20 - Improvements to Eroor-Kaniyampuzha road ch.0/400 to 0/800 and junction and road improvements near to Vytilla Mobility Hub | 50 | Tendering procedure in progress.Price Id 4209.
Constituency:Piravam |  | 200
1 | Budget work 2019-20 - Improvements to Chithrapuzha road from ch.0/000 to 1/540 | 140 | Tendered
Constituency:PARAVUR nil
Constituency:Ernakulam
1 | Budget work 2019-20 - Improvements to Chittoor Moolampilly Road Ch.0/000 to 1/000 | 75 | Tendered with opening as on 15.11.2019
2 | Budget work 2019-20 - Improvements to Aluva Ernakulam Road (From MG Road Medical Trust to Thevera) | 25 | Work in progress
3 | Budget work 2019-20 - Improvements to Old NH (Between Naval Base to BOT Bridge) | 100 | Estimate submitted for TS
200

## NABARD
CONSTITUENCY WISE LIST OF ROAD WORKS SANCTIONED DURING THIS MINISTRY WITH PRESENT STATUS
Sl. No | Name of work | Amount of work in Lakhs | Present Status of work
Division:Ernakulam(NABARD)
Constituency: Paravur
| NABARD-RIDF -XIX-Improvements and providing BM & BC resurfacing to kodungallur -Athani-Nedumbassery Airport road(Part II) between ch.8/000 to 18/000 | 1200 | Work completed
Constituency: Aluva
| NABARD - RIDF- XXIV-Improvements to Chengmanad Elavoor Road ch.0/000 to 7/450 | 1100 | DLP of SLTF works will expired only on 15.11.2.019. TS estimate returned from CE's office for correction is to be resubmit soon
Constituency:Paravur/Kalamassery
| NABARD - RIDF- XXI - Improvements to Vedimara Athani Road in Ernakulam District | 1500 | Work completed.
Constituency: Aluva/Kalamassery
| NABARD - RIDF- XXI - Improvements to Aluva Paravur Road Ch. 3/000 to 15/500 in Ernakulam District | 1200 | Work completed.
Constituency: Thripunithura
| NABARD - RIDF- XXII-Providing BM &BC to Ettumanoor -Ernakulam Road CH.44/200 TO 46/900 | 250 | Work Completed.
Constituency: Piravam
| NABARD - RIDF- XXIV-Improvements to Ugayamperoor Kureekad Road ch.0/600 to 1/600 and Kottayathupara-Kureekad-Thuppumpady road Ch.0/000 to 2/980 | 500 | S.N issued